PROJECT MANAGEMENT · MONTHLY PROJECT REPORT [Project Name] [Street Address, Suburb QLD Postcode]

Document Monthly Project Report No. [NN] Date [D Month YYYY] Prepared for [Principal] Prepared by Bentley Development Management Reference [Project No.] · MR-[NN] Revision R0 · DRAFT — NOT FOR ISSUE

1.0  Report particulars

| Item | Detail |
| --- | --- |
| Project | [Street Address, Suburb QLD Postcode] |
| Period | [Period start] to [period end] · data cut-off [D Month YYYY] |
| Stage | [Project stage — e.g. design development, pre-approval, pre-contract] |
| Approvals | [Approval refs — e.g. MCU/YYYY/NNN (Council) · SARA ref] |

2.0  Status summary

[Position at period end] with movements to the [data cut-off] data cut-off. Ratings are BDM’s assessment of residual risk. Critical risks at Annexure A, outstanding actions at Annexure B.

| Section | Position | Status |
| --- | --- | --- |
| 3.0 Programme | [One-line position for this section] | [LOW / MEDIUM / HIGH] |
| 4.0 Cost | [One-line position for this section] | [LOW / MEDIUM / HIGH] |
| 5.0 Approvals | [One-line position for this section] | [LOW / MEDIUM / HIGH] |
| 6.0 Design | [One-line position for this section] | [LOW / MEDIUM / HIGH] |
| 7.0 Construction and delivery | [One-line position for this section] | [LOW / MEDIUM / HIGH] |

3.0  Programme

Programme [file and revision] of [date], read from the native file. [State whether it carries a status date and whether activity has been statused — if not, float is an as-planned value.]

| Key milestone | Programmed finish | Float | Position at 4 August 2026 |
| --- | --- | --- | --- |
| [Key milestone 1] | [Programmed finish] | [Float] | [Position at data cut-off] |
| [Key milestone 2] | [Programmed finish] | [Float] | [Position at data cut-off] |

—	Critical path: [activity] → [activity] → [activity] → Construction Commencement. [Programme currency note and any reissue recommendation.]

4.0  Cost

Reported on the BDM Form 425 development-summary basis. [State which lines carry verified data and which do not.] All figures exclusive of GST.

4.1  Development budget

| Development cost | Approved budget | Variations | Forecast cost | Cost to date | Cost to complete |
| --- | --- | --- | --- | --- | --- |
| Land | n/e | n/e | n/e | n/e | n/e |
| Professional fees | n/e | n/e | n/e | n/e | n/e |
| Authority fees and charges | n/e | n/e | n/e | n/e | n/e |
| Construction | n/e | n/e | n/e | n/e | n/e |
| Contingency | n/e | n/e | n/e | n/e | n/e |
| TOTAL DEVELOPMENT COST | n/e | n/e | n/e | n/e | n/e |

n/e — not established. [Where no cost plan or development budget exists, say so and state the consequence: no total development cost or cost to complete can be reported.]

4.2  Professional fees — cost to date and cost to complete

| Category | Forecast fee | Cost to date | Cost to complete | Status |
| --- | --- | --- | --- | --- |
| Executed agreements | [$] | [$] | [$] | [Consultants / source] |
| Accepted, agreement pending | [$] | [$] | [$] | [Consultants / source] |
| Issued, unexecuted | [$] | [$] | [$] | [Consultants / source] |
| Proposal only, not engaged | [$] | [$] | [$] | [Consultants / source] |
| Not quantified | [$] | [$] | [$] | [Consultants / source] |
| TOTAL | [$] | [$] | [$] | [Consultants / source] |

4.3  Cost movement this period

| Element — change of electrical consultant | Amount ex GST | Position |
| --- | --- | --- |
| [Element 1] | [$ ex GST] | [Position] |
| [Element 2] | [$ ex GST] | [Position] |

[Contingent items — part-performed scopes, amounts that may be reinstated, and the worst-case net position.]

5.0  Approvals

| Approval | Reference | Status at 4 August 2026 |
| --- | --- | --- |
| [Approval 1] | [Reference] | [Status at data cut-off] |
| [Approval 2] | [Reference] | [Status at data cut-off] |

6.0  Design

| Discipline / item | Status at 4 August 2026 |
| --- | --- |
| [Discipline / item 1] | [Status / position at data cut-off] |
| [Discipline / item 2] | [Status / position at data cut-off] |

7.0  Construction and delivery

[Where there is no construction activity, contract or executed ECI agreement, say so — and state that there are accordingly no claims, variations, EOTs, notices or defects. Do not delete this section.]

| Pre-construction item | Position at 4 August 2026 |
| --- | --- |
| [Pre-construction item 1] | [Status / position at data cut-off] |
| [Pre-construction item 2] | [Status / position at data cut-off] |

ANNEXURE A

Critical risk register

Critical (HIGH-rated) risks only, in order of priority, at [data cut-off].

| # | Risk | Position and mitigation | Rating |
| --- | --- | --- | --- |
| R1 | [Risk] | [Position and mitigation] | [HIGH] |
| R2 | [Risk] | [Position and mitigation] | [HIGH] |

Also monitored, rated MEDIUM: [one-line summary of each MEDIUM-rated item, in prose, not tabulated].

ANNEXURE B

Outstanding actions

| # | Action | Responsibility | Due |
| --- | --- | --- | --- |
| 1 | [Action] | [Responsibility] | [Due] |
| 2 | [Action] | [Responsibility] | [Due] |
| 3 | [Action] | [Responsibility] | [Due] |

END OF REPORT